Executive Summary

Review of the flagship programmes was held by Sr. Adviser (State Plans_Puducherry)-, in a meeting with the Chief Secretary and other state Government officials in Puducherry, followed by a field visit to Karaikal.  Overall it was observed that:

- Flagship programmes in the Education and Health sectors were being implemented efficiently.

- Puducherry was not availing any assistance under most of the schemes under Bharat Nirman Programme since it had already achieved the milestones which were essential for being eligible for assistance under programmes such as PMGSY, RGGVY, APDRP etc.

Major observations

NREGS started in Puducherry in 2008-09.  Since the programme started last year, it could not utilize the funds fully in 2008-09.  Out of Rs.5.80 crore, the total expenditure was only 1.64 crore in 2008-09. The programme is gradually picking up in the current year.

Under NRHM though the infrastructure was good and physical targets were being achieved the UT was a laggard in achieving financial outlays. It was reported that this was due to the lag in the construction work of the buildings.

The Mid Day Meal scheme and Sarva Shiksha Abhiyan schemes operated well in Puducherry. MDM example of clean centralized kitchens could be emulated by other states. The UT requested that the Government of India may also provide Assistance for the extension of the Scheme to the students of IX to XII Std. besides the children of Pre-Primary Classes.  Further, the quality of rice supplied under Midday Meal Scheme may be improved and it was also suggested that Grade Rice should be made available instead BPL Rice under Midday Meal Scheme.

Under Indira Awaas Yojana and Total Sanitation Programme, the progress is slow as the state has a better scheme for housing and construction of toilets under which subsidy component for the beneficiaries is more attractive than available under these two centrally sponsored schemes.

It was reported that JNNURM is suffering due to the procedural delays.

National Horticulture Mission NHM) has been accorded approval in Puducherry during 2009-10 with a total outlay of Rs.133.50 lakh Puducherry Horticulture Society has been established as per the guidelines of the NHM and registered under the Societies Registration Act. Applications have been received from the farmers seeking assistance under various components of the scheme.

Other Observations

The Karaikal Port set up in the PPP mode is the single largest PPP project taken up by the State Government (along with the airport coming up in Karaikal) and two berths in the port were put up in a record time and commercial operation has already started. This port will play a very important role in economic development of the state.

During the last two years, the actual Plan expenditure of Puducherry has remained around Rs.1000 crores as against the approved outlays of Rs.1455 crore and Rs. 1750 crores.  For a state with very small population base and with practically no source of revenue, additional resource mobilization poses a problem.

The State has more number of BPL cards than there are families and support in the nature of subsidised food, items of household use, additional funding for pension schemes and additional funds under education, health and other activities have come to be established in the State.

The only way that the ballooning of expenditure under the welfare schemes can be controlled is to critically review the beneficiary group and consciously prune the population who are not poor or deserving.  This may lead to some savings which can be ploughed back to developmental activities.

Puducherry has a tremendous potential for tourism and there are several spots under the ownership of the Government, both at Kariakal and Puducherry where hotels and other tourist complexes can be developed in the PPP mode.  Similarly, large chunks of acquired land are also available very close to the port, which can be developed into a remunerative industrial hub.  Both these activities can be taken up with the state working as a facilitator.

There is also a huge workforce mostly in the textile sector whose output has steadily declined over the years.  As opposed to that in many areas of Government work, the work is suffering for want of manpower. The state should come out with a proper manpower deployment policy so that both the numbers and the financial commitment are frozen or reduced.

Implementation of the Flagship programmes in Puducherry -report

I along with Director (State Plans-Puducherry), Ms. Sujata Sharma visited Puducherry from 3.12.2009 to 5.12.2009 to review the implementation of the flagship programmes. Review of all flagship programmes was held in Puducherry in a meeting with the Chief Secretary and other state Government officials, followed by a field visit to Karaikal.  Overall it was observed that:

- Flagship programmes in the Education and Health sectors were being implemented efficiently

- Puducherry was not availing any assistance under most of the schemes under Bharat Nirman Programme since it had already achieved the milestones which were essential for being eligible for assistance under programmes such as PMGSY, RGGVY, APDRP etc.

Overview of the Performance under the Flagship Programmes

In the following table an overview of the physical and financial targets and achievements under various flagship programmes have been outlined.

| Financial Progress (Outlay & Expenditure) Rs. in lakhs |
| --- |
| Sl. No. | Name of the Scheme | Outlay (Mission pd *) | Annual Plan 2007-08 | Annual Plan 2008-09 | Annual Plan 2009-10 |
|  |  |  | Oulay 2007-08 | Expenditure | Outlay 2008-09 | Expenditure | Outlay 2009-10 | Expenditure (upto October '09) |
| 1 | National Rural Employment Gurantee Scheme (NREGS) |  | 0.00 | 0.00 | 580.23 | 164.74 | 415.49 ** | 337.79 |
| 2 | Indira Awaas Yojana (IAY) |  | 79.28 | 42.19 | 37.87 @ | 24.37 | 13.50 | 19.20 |
| 3 | National Social Assistance Programme (NSAP) |  | 115.00 | 115.00 | 168.00 | 168.00 | 264.00 | 0.00 |
| 4 | National Rural Health Mission (NRHM) |  | 1222.97 | 415.35 | 1411.87 | 532.65 | 1031.23 & | 602.23 |
| 5 | Integrated Child Devt Scheme (ICDS) |  | 178.29 | 173.83 | 200.00 | 254.44 | 367.68 | 217.65 |
| 6 | Accelerated Rural Water Supply Progr. (ARWSP) |  | 3.01 | 3.01 | 8.68 | 8.68 | New proposals for 3works for Rs.14.30 crores sent to GOI |
| 7 | Central Rural Sanitation Programme (CRSP) |  | 40.10 | 7.94 | 32.26 | 7.46 | 24.80 | 7.50 |
| 8 | Mid Day Meals (MDM) |  | 913.63 | 913.63 | 1051.60 | 996.83 | 1187.72 | 359.31 |
| 9 | Sarva Shiksha Abhiyan (SSA) |  | 893.50 | 629.23 | 1313.68 | 1122.73 | 1246.36 | 386.72 |
| 10 | Jawahar Lal Nehru Nat. Urban Renl Mission (JNNURM) | 19252.00 | 6264.00 | (#) | 1505.65 | (#) | 6502.50 | 429.35 |
| 11 | National Horticulture Mission (NHM) |  | -- | -- | -- | -- | 133.50 | -- |
| * | Information with the concerned Central Ministries and the same is not available with the UT | ** | Carry forward amount from last year; |
| & | Carry forward amount from last year | @ | Outlay includes previous year balance, current year release & Other receipts |
| # | Amount taken to Public Accounts of Govt. of UT |  |  |

| Physical Targets and Achievements |
| --- |
| Sl. No. | Name of the Scheme | Units | Physical Targets | Achievements |
|  |  |  | 2007-08 | 2008-09 | 2009-10 | 2007-08 | 2008-09 | 2009-10 upto October '09) |
| 1 | National Rural Employment Gurantee Scheme (NREGS) | No. of Mandays (In lakhs) | -- | 5.00 | 13.42 | - | 1.65 | 4.68 |
| 2 | Indira Awaas Yojana (IAY) | Number of Houses | 300 | 300 | 330 | 101 | 52 | 22 |
| 4 | Integrated Child Development Scheme (ICDS) | No. of ben.s (Mothers) | 9000 | 9300 | 10000 | 9482 | 9015 | 8992 |
|  |  | No. of ben. (Children) | 30000 | 29000 | 30000 | 29910 | 28315 | 24761 |
| 5 | Operationalization of ICDS Projects | Nos. | 5 | 5 | 5 | 5 | 5 | 5 |
| 6 | Operationalization of Anganwadi Centres | Nos. | 688 | 688 | 788 | 688 | 688 | 688 |
| 8 | Total rural Sanitation Camp.CRSP) | Individual | * | * | * | 258 | 219 | 230.00 |
|  |  | Community | ** | ** | ** | 2 | 2 | -- |
| 9 | Mid Day Meal (MDM) | No. of students | 126000 | 126000 | 130000 | 126000 | 126000 | 130000 (Estimated) |
| * | For the project period, Individual Toilets Targets: 18,000; Achievement made so far 2134 |
| ** | For the project period, Community Toilets Targets: 26; Achievement made so far 38 |

- NREGS started in Puducherry in 2008-09 and work on preparation of basic infrastructure for the implementation of the programme was in progress.  Since the programme started last year, it could not utilize the funds fully in 2008-09.  Out of Rs.5.80 crore, the total expenditure was only 1.64 crore in 2008-09. The programme is gradually picking up in the current year.

- Under IAY and TSC programmes, the progress is slow as the state has a better scheme for housing and construction of toilets under which subsidy component for the beneficiaries is more attractive than available under these two centrally sponsored schemes.

- Under NRHM though the infrastructure was good and physical targets were being achieved the UT was a laggard in achieving financial outlays. It was reported that this was due to the lag in the construction work of the buildings.

- The Mid Day Meal scheme and Sarva Shiksha Abhiyan schemes operated well in Puducherry. MDM example of clean centralized kitchens could be emulated by others

- It was reported that JNNURM is suffering due to the procedural delays.

Progress / issues in the implementation of the programmes Observations during field visit in Karaikal, Puducherry

National Rural Employment Guarantee Scheme (NREGS)

This programme is being implemented in Karaikal region of the U.T since 60% of the rural area are in Karaikal only. The main activity undertaken through NREGS funds was desilting of canals, since the canals had water for only three months and for the rest of the year they were without water. On enquiry, the district officers informed that prior to NREGA Rs. 50 lacs was earmarked by PWD for desilting of the canals every year, now under NREGA the expenditure was Rs. 3.00 crores so far this year. APL households were also participating under NREGS.  About 30,000 job cards have already been issued. The district has already exhausted its allocation and wanted more funds.

Observations during the field visit, Karaikal

It was seen that heavy investment was being incurred by the district on the desilting and weeding of the canals every year, therefore, permanent lining of the canals should be done in next 2-3 years and NREGA funds should be utilized for other activities which may lead to creation of permanent assets. There was no need to spend a large chunk of funds of NREGS for desilting of canals every year. More innovative works, if need be included individual beneficiary programmes.

National Rural Health Mission (NRHM)

It was observed that the expenditure under NRHM has been low over the last three years. It was informed that the health infrastructure was good in Puducherry and physical targets were almost being fully met under NRHM.  The UT officers informed that the unspent balances were due to the time lag in the construction of buildings because of which the money was lying unspent.

The TRP in the current year was of Rs.16.00 cr. excluding the state share where as the expenditure was only Rs.6 crs. including the advances. It is very likely that this year too the expenditure will be low unless remedial action is taken.

It was also observed during the meeting that the progress on the construction of Mother and Child hospital in Puducherry was pending for the last 2-3 years.  Since TRP funds have been made available for the completion of the hospital it should be completed by the end of this financial year.

Observations during field visit in Karaikal

District indicators, Karaikal, (2001 Census)

| Indicators | Census 2001 |
| --- | --- |
| Population (in thousands) | 171 |
| Decadal Growth Rate (1991-01) | 17.1 |
| Sex Ratio* | 1,022 |
| Percent Urban Population | 43.5 |
| Female Literacy Rate (7 years and above) | 74.7 |
| Male Literacy Rate (7 years and above) | 89.4 |

Sample outcome, DLHS – 3, 2007-08

| Category | No. covered | Response Rate |
| --- | --- | --- |
| Households | 1,089 | 99.0 |
| Married Women (15-49 years) | 898 | 96.9 |
| Unmarried Women (15-24 years) | 296 | 97.4 |
| Sub Centres | 15 | 100 |
| Primary Health Centres (PHC) | 8 | 100 |
| Community Health Centre (CHC) | 1 | 100 |
| District Hospital (DH) | 1 | 100. |

School Health Programme was started with public private partnerships (Vinayaga Mission Medical College) during 2008. School Health Examinations are being done by the Pediatric PG students of Vinayaga Mission Medical College. Karaikal. They have examined about 23,000 school children. They are paid Rs.8+2. Each Medical officer will examine 50 students per day. Blood Test and HB test will be done for anaemic students.

In Karaikal region the statistics of the population is as follows:

No. of Students  			- 	                      23,000

No. of students examined in school	- 		8,000

Health data maintained for students	-		3,500

- A special health card was designed with the help of specialist (medical / computer) and software developed with the help of NIC.

- Referral children are referred to GH in a vehicle and RMO of GH Karaikal receives them and does the necessary investigation.  The PHC medical officers of respective areas follow the students who require follow up treatment.

- The Innovative School Health Programme provides medical checkup, investigation, treatment, anti-worm therapy and follow up treatment.

Visit to Melakasakudy sub-centre

A visit to Melakasakudy sub-centre was also paid along with the district level officers to observe the implementation of NRHM programme in the field.  The following indicators were observed for the sub-centre in Melakasakudy sub-centre.

|  | Male | Female | Total |
| --- | --- | --- | --- |
| Population of the Villages covered by the Sub-centre | 1647 | 1733 | 3380 |
| Children 0-5 years | 154 | 138 | 292 |
| Birth Rate |  | 15 |
| No. Middle schools |  | 2 |
| No. of Anganwadis |  | 4 |

This sub-centre catered to four Anganwadis for the implementation of ICDS programme.  The infrastructure in the form of building, medicine and furniture was found to be clean and well maintained.  Two ANMs were serving at the sub-centre.  The working of the sub-centre appeared to be good and no problems were mentioned by the staff of the sub-centre.

Field visit to an upgraded PHC, Karaikal

The visit was paid to the upgraded PHC in Karaikal.  Out of six doctors present, three were hired on contractual basis under NRHM. The district collector informed that the infrastructure was not a problem in Karaikal but the quality of infrastructure needed to be upgraded.

Response of the Beneficiaries

The visit to the wards was made and two patients were suffering from tuberculosis and gastro ailments were contacted. The patients informed that the treatment, medicines and meals were made available at the PHC. Both the patients came from the nearby Tamil Nadu State.  In Karaikal district a lot of migrant population was observed to be crossing over to Puducherry for treatment because of the vicinity and easy availability of treatment in Puducherry.

# Indira Awaas Yojana (IAY)

The performance of the IAY since 2004-05 is indicated below:

| Year | Target | Houses constructed |
| --- | --- | --- |
| 2004-05 | 629 | 88 |
| 2005-06 | 333 | 235 |
| 2006-07 | 300 | 261 |
| 2007-08 | 300 | 101 |

Observations

It was informed by the UT officers that the UT Government is having a better scheme called Kamraj Housing Scheme.  The beneficiaries find the State’s sector scheme more attractive since the amount of subsidy provided under the State scheme is higher than that available under IAY.  Moreover, states’ scheme is sanctioned very fast without many procedural requirements. Therefore, it was not possible for the beneficiaries to avail the benefits of IAY.

Kamaraj Housing Scheme (State scheme) launched in 2006-07, had a subsidy of Rs.1.00 lakh, and so state assistance under IAY was increased to Rs.75,000/- per house to have parity with the  Kamaraj Housing Scheme.  For the beneficiaries the IAY scheme is unattractive and it necessitates bringing parity between IAY Scheme and the Kamaraj Housing Scheme.

- The higher amount offered by the State housing Scheme, ensured that the public migrated to the Kamaraj Housing Scheme.

- Besides Adi-dravidar Welfare department has been implementing a Housing Scheme for SCs with Rs.2.00 lakhs subsidy per beneficiary which made the I.A.Y. scheme still more unattractive.

Major issues in IAY highlighted by the UT

- Cumbersome procedures

MORD mandated that it would give IAY funds only on the basis of the BPL list being prioritized and put up Village Panchayats wise. Two lists have to be prepared, out of all eligible BPL families within the Gram Panchayat viz. (1) Priority list of SC/ST  BPL families and (2) Priority list for poor  BPL families of non SCs. Each list is in ascending order of score of BPL census. The poorest family would find a place at Sl.No.1 and thereafter it was to follow the score based ranking in the ascending order. Beneficiaries are to be selected only in the order indicated in the list for assistance under IAY. With regard to BPL wait list of this U.T, the BPL survey was started in 2003 and completed in 2005 when there were no village panchayats. The software platform developed for the purpose did not provide for Village Panchayats entry and as such, there were tremendous difficulties in developing the village Panchayats wise BPL list.

- Problem of the BPL households

For strict implementation of IAY selection through BPL Lists, it has been seen that, the poorest of the poor are unable to construct a house because (1) he does not own the land and (2) has very little means to complete it. He is eligible only because his name is amongst the poorest of the poor in the village. Moreover, the present escalation in building materials especially steel and cement is the major impediment for them to construct the pacca houses within subsidy alone.

Total Sanitation Programme (TSC)

TSC was introduced as a Project Mode implementation in the place of the Central Rural Sanitation Programme from 2001-02. Rs.1500/- is given as subsidy for constructing a toilets in this programme. It was informed that owing to the present rate of inflation in material costs, the drastic reduction in the subsidy completely reduced the demand in rural areas.

Major Issues under TSC reported by the UT

- The UT has a more attractive scheme called Perunthalaivar Kamarajar Centenary Housing scheme. Under this scheme, an amount was Rs.10,000/- is given for construction of a Toilet. That is why the number of toilets constructed under the central scheme TSC fell drastically.

- Hence, in Puducherry special efforts have to be taken to enhance the subsidy for the construction of individual toilets i.e. provision of additional state incentive of Rs.2500/- along with Central subsidy of Rs.2500/-. Already, through propaganda, nearly 3000 applications were received by DRDA. It is proposed to give construction subsidy for construction of 1000 individual latrines during 2009-10 with the available funds on hand.

- In respect of Community Sanitary Complex, continuous maintenance is a problem. No funds are available for routine maintenance and the poor maintenance results in the toilet blocks falling into disuse.

Mid Day Meals Scheme

In Puducherry, the Midday Meal Scheme is being implemented from Pre-Primary to XII Std. as detailed below:

State / Central Share:           I –VIII Std.

Only State Share:	             Pre-Primary & IX-XII Std.

- Mid Day Meal Scheme provided to all children from Pre-Primary level to Class XII. About 1.26 lakh students are covered under the scheme in all Government and Government aided schools out of Central Assistance and the State Resources.

- In Puducherry, daily menu contains 130/160 grams of Rice, Sambar with Vegetable Poriyal at primary and upper primary levels respectively and 75 grams of vegetables per day/student. Boiled eggs are given twice in a week. However, the Government of Pudcherry bears the cost of 30/10 grams of additional rice at primary and upper primary levels respectively.

- The Unit Cost of Mid Day Meal for classes I –V is Rs.4.00 on Vegetable day and Rs.5.55 on egg day.

Achievement in 2008-09 and Expected coverage in 2009-10

| Achievement during 2008-09 |
| --- |
|  | Total | Achievement | Shortfall |
| Children at primary stage | 60485 | 54630 | 5855 |
| Children at Upper primary stage | 47729 | 41326 | 6403 |
| Expected Achievement during 2009-10 |
|  | Total | Achievement | Shortfall |
| Children at primary stage | 61200 | 55737 | 5463 |
| Children at upper primary stage. | 48300 | 42375 | 5925 |

Central Assistance                                                (Rs. in lakhs)

| Expenditure during 2008-09 | Borne by the Central Govt. | Borne by the U.T. | Total Expenditure(so far) |
| --- | --- | --- | --- |
| Cost of food grains (Free Rice / Open market Rice) | 128.58* | 56.88** | 185.46 |
| Transportation cost | 17.06 | 1.95 | 19.01 |
| For kitchen-cum-store | 55.20*** | 0 | 0 |
| For Kitchen devices | 0 | 3.05 | 3.05 |
| Total | 200.84 | 61.88 | 207.52 |

Note : * In the year 2008-09, a total quantity of 2275.805 MTs of free Rice was lifted and the cost of the same as per the records are Rs.128.58 lakhs

** A total quantity of 360MTs of Rice was procured in the co-operative institutions at the rate of Rs.15.30 / Kg. and the total cost of 360 MTs of Rice was Rs.56.88 lakhs.

*** The concept of the cooking the Mid-day Meal in the modernized Central Kitchens is being followed in Puducherry.  The amount of Rs.55.20 lakhs provided for the  construction of kitchen-cum-store is proposed to be utilized for the construction of a Central Kitchen at Kuruvinatham in Puducherry at a cost of Rs.200.00 lakhs (i.e. Central share – Rs.55.20 lakhs and State Share – Rs.144.80 lakhs).

Norms for Central Assistance

| Center State Sharing Pattern |
| --- |
|  | Total cost per meal | Centre | State |
| Primary | Rs.4.00 (Non-egg day) Rs.5.55 (Egg day) | Rs.1.58 Rs.1.58 | Rs.2.42 (Non egg day) Rs.4.17 (Egg day) |
| Upper Primary | Rs.3.69 (Non-egg day) Rs.5.44 (Egg day) | Rs.2.10 Rs.2.10 | Rs.1.59 (Non egg day) Rs.3.34 (Egg day) |

Cooking cost includes the cost of pulses, vegetables, oil, condiments, fuel and labour and administrative charges.

Implementation of the scheme in Puducherry as reported by the UT

The Department of School Education is directly implementing the scheme in Puducherry.  There are 12 Central Kitchens functioning at present besides 92 School Canteen Centres.   1 Mega Kitchen with a feeding strength of 20,000 students at Lawspet, Puducherry is under construction and likely to be activated in May 2010.  The Chief Educational Officer, Puducherry, Karaikal, Mahe and the Delegate to the Director of School Education, Yanam are the Nodal officers for the implementation of the scheme in Puducherry.

Role of teachers

The Head of Institutions appoint teachers for the supervision of meals on rotation basis without affecting their teaching and learning process. Before distribution the teaching staff on supervisory duty shall taste the meal to ascertain the quality.

Management & supervision: School level

- Regularity / wholesomeness of meal; cleanliness in distribution/cooking

- Timeliness in purchase of good quality ingredients, fuel

- Foster social and gender equity.

- The Head of Institution is also bearing the responsibility of manning the kitchens located in the schools as part of their Administrative works as they have to handle classes only for 10 periods per week.

Guidelines have been issued to implement the scheme in an error free manner.

Experience of the UT after implementation of the programme

- The enrolment is gradually increasing.

- The drop-out ratio in Primary level is reduced.

- The dropout ratio in Upper primary level is reduced to 3% in the year 2007-08 from 7.16% in the year 2004-05

- The Union Territory of Pondicherry is ranking first in the composite Educational Development Index (EDI) for both Primary and Upper Primary for the year 2007-08

- Gender Parity Index in Enrolment is 0.98 in the year 2007-08 and whereas it is 0.93 in the National level

- Gender Parity Index in Enrolment for Upper Primary is 0.96 in the year 2007-08 and whereas it is 0.89 in the National level

It was informed that the delegates from other States like Kerala and Goa and the neighbouring countries like Nepal have visited Puducherry to observe the implementation of the scheme (since only in Puducherry the scheme is being implemented with a high degree of quality by cooking the meals in the modernized central kitchens)

Suggestions of the UT to improve the programme

- The Government of India may also provide Assistance for the extension of the Scheme to the students of IX to XII Std. besides the children of Pre-Primary Classes.

- Further, the quality of Rice supplied under Midday Meal Scheme may be improved and it is also suggested that Grade Rice should be made available instead BPL Rice under Midday Meal Scheme.

- The scheme may be implemented in SSA pattern by a separate Society to make accountability in a more effective manner.

The visit to upper primary school was paid in Karaikal district. The infrastructure in the form of building was in good condition.  The class rooms were also clean and well maintained.  The implementation of Mid Day Meal scheme was observed in which rice, sambhar, vegetable and eggs were being served to the children. It was informed that the cooking cost was coming to Rs.4.00 per child.  The eggs were served twice a week when the cost of the meal increased by Re.1.  The food was cooked in a separate kitchen through fire wood and the school requested that free gas should be supplied to the school to reduce the cooking cost.  The Government should strongly consider the request of the school for providing free gas to the Mid Day Meal scheme.

Sarva Shiksha Abhiyan (SSA)

i) Enrolment GER and NER (2008-09)

| Stages | Enrolment | GER % | NER % |
| --- | --- | --- | --- |
|  | Boys | Girls | Total | Boys | Girls | Total | Boys | Girls | Total |
| Primary | 58041 | 54643 | 112684 | 113.2 | 111.6 | 112.4 | 100.74 | 99.23 | 99.98 |
| Upper Primary | 36328 | 33483 | 69811 | 109.9 | 104.0 | 107.0 | 91.12 | 89.13 | 90.15 |

Funds released for SSA by Government of India and State

| Year | GOI Share released (Rs. in lakhs) | State Share released (Rs. in lakhs) |
| --- | --- | --- |
| 2006-07 | 0.00 | 100.00 |
| 2007-08 | 577.07 | 142.00 |
| 2008-09 | 638.60 | 277.00 |
| 2009-10 (Latest) | 273.96 | 0.00 |

Major Interventions approved for 2008-09 and 2009-10

| Sl.No. | Activities | 2008-09 | 2009-10 |
| --- | --- | --- | --- |
|  |  | Target | Achievement | Target | Achievement so far |
| 1 | School Buildings | 10 | 03 In progress | 02 | - |
| 2 | Additional classes (Primary + Up. Primary) | 108 | 108 In progress | 76 | 23 In progress |
| 3 | Drinking water | - | - | - | - |
| 4 | Toilets | 26 | 19 | 10 (7 + 3) | 07 |
| 5 | Major Repairs | - | - | - | - |

| S.No | Name of the Scheme | Physical Targeats | Achievements |
| --- | --- | --- | --- |
|  |  | 2007-08 | 2008-09 | 2009-10 | 2007-08 | 2008-09 | 2009-10* |
| 1 | Teachers salary | 32 | 38 | 44 | 18 | 23 | 24 |
| 2 | Civil Works | 177 | 422 | 3088 | 151 | 422 | 664 |
| 3 | Block Resource Centre | 6 | 6 | 6 | 6 | 6 | 6 |
| 4 | Cluster Resource Centre | 25 | 25 | 25 | 0 | 3 | 3 |
| 5 | Teacher Grant | 4742 | 4864 | 4114 | 4630 | 4864 | 1689 |
| 6 | School Grant | 580 | 578 | 590 | 535 | 573 | 572 |
| 7 | Repairs & Maintenance Grant | 580 | 498 | 508 | 499 | 498 | 505 |
| 8 | Integrated Education for Disabled | 2701 | 2983 | 2926 | 2501 | 2983 | 942 |
| 9 | Interventions for Out-of-school children | 2673 | 892 | 646 | 350 | 559 | 40 |
| 10 | Research & Evaluation | 456 | 578 | 590 | 456 | 578 | 53 |
| 11 | Remedial Teaching | 8069 | 7190 | 6990 | 6456 | 7190 | 250 |
| 12 | Teaching Learning Equipment | 10 | 5 | 2 | 4 | 5 | 2 |
| 13 | Teacher Training | 4807 | 4929 | 8323 | 3436 | 3758 | 2649 |
| 14 | Training of community leaders | 1970 | 1438 | 94 | 994 | 490 | 555 |

Sarva Shiksha Abhiyan (SSA) was implemented in Puducherry and activities under SSA included not only the construction of class rooms and appointment of teachers etc. but to provide a computer lab in every school.  The hardware was procured but the software was developed for the students’ curriculum by the Aziz Premji Foundation.

Field visit to upper primary school in Karaikal district

It was observed that the children were taught by the ‘activity based learning’ method upto class III, and teachers found this innovative method to be more practical and effective.

JNNURM

| No. of Mission Cities Selected under JNNURM =1 | Name of Cities Puducherry Town of the U.T. | Date of CDP Submission 2-3-2007 |
| --- | --- | --- |

| Sl. No. | Name of the Projects/Activites | Approved Outlays (Rs. in crores) | Expenditure (Rs. in crores) |
| --- | --- | --- | --- |
|  |  | 2007-08 | 2008-09 | 2009-10 | 2007-08 | 2008-09 | 2009-10 |
| I. | Sub-mission for Urban Infrastructure And Governance |  |  |  |  |  |  |
|  | Name/location of the project |  |  |  |  |  |  |
| 1. | Comprehensive Sewerage scheme for Puducherry | 50.85 | 0.197 | 2.63 | NIL | NIL | NIL |
| 2. | Integrated Solid Waste Management System for Puducherry | NIL | 12.415 | 3.2743 | NIL | NIL | NIL |
| 3. | Purchase of 50 buses under JNNURM | NIL | NIL | 8.075 | NIL | NIL | NIL |
| II. | Submission for Basic Services for Urban Poor |
|  | Name/location of the Project |  |  |  |  |  |  |
| 1. | Construction of 1136 Dwelling units at Lambert Saravanan Nagar, Reddiarpalayam, Puducherry | 8.7685 | 0.5753 | 7.6511 | NIL | NIL | 2.00 |
| 2. | Construction of 168 Dwelling units at Kuruchikuppam, Puducherry | 1.3296 | 0.3206 | 1.6486 | NIL | NIL | 1.974 |
| 3. | Construction of 1660 Houses for SC Beneficiaries at 17 Locations in Puducherry | NIL | NIL | 13.9582 | NIL | NIL | NIL |
| Total | 60.9481 | 13.5079 | 37.2372 | NIL | NIL | 3.974 |

Progress and suggestions of the UT to improve the implementation of the JNNURM:

- The project “Comprehensive Sewerage System for Urban areas of Puducherry” was approved in the CSMC meeting of MoUD, Government of India held on 24.2.2007 at an estimate cost of Rs.203.40 Cr.  The tendered amount of the project is Rs.282.17 Cr.  The Govt. of Puducherry has addressed to Ministry of Home Affairs, GOI, to authorise the Lt. Governor of Puducherry to accord expenditure sanction for a total amount of Rs.282.17 Cr.  The Ministry of Home Affairs, GOI has referred the matter to the Ministry of    Urban Development (MoUD), GOI on 11.11.2009 for concurrence and opinion.  The project will be taken up soon after receiving reply from the Ministry of Home Affairs.

- The Planning Commission has increased the allocation under UIG sub-mission to Rs.262.72 Cr. from the earlier allocation of Rs.162.72 Cr. for the Mission period. Projects worth of Rs.202.45 crores has been approved under UIG sub-mission.  However, the allocation under Urban Infrastructure Development Scheme for Small and Medium Town (UIDSSMT) has not been increased.  Since, funds are required for the projects worth of Rs.125.00 Cr. for Karaikal region (water supply & sewerage), the balance allocation available under UIG sub-mission has to be diverted to UIDSSMT sub-mission (Rs.60.27 Crores).

- Under Basic Services for Urban Poor, the original allocation of ACA was Rs.73.20 Crores and the same has been revised to Rs83.20 crores.  Similarly, the allocation made under IHSDP sub-mission has been revised from Rs.6.95 crores to Rs.26.95 crores.  Since, projects worth of Rs.50.00 crores under BSUP sub-mission have to be executed, the BSUP allocation may be increased from Rs.83.20 Cr.  to 103.20 Cr. by diverting additional allocation made under IHSDP.

- The funds for the purchase of buses under Urban Transport System is yet to be released by the Ministry of Home Affairs, Government of India

National Horticulture Mission

Government of India has accorded approval for the implementation of the scheme “National Horticulture Mission” in this Union Territory during 2009-10 with a total outlay of Rs.133.50 lakh, out of which 85% (Rs.113.50 lakhs) is the Central Share 15% is the State Share (Rs.20.00 lakhs. At the first instance, Government of India has sanctioned an amount of Rs.33.25 lakhs. Puducherry Horticulture Society has been established as per the guidelines of the National Horticulture Mission and registered under the Societies Registration Act. Applications have been received from the farmers seeking assistance under various components of the scheme.

The financial target of Rs. 33.25 lakhs sanctioned at present by the Government of India will be achieved during the main vegetable season of Thai Pattam (January 2010). Further, action is underway to establish cold storage unit by calling E.O.I from established firms.

Observations

Under this programme funds were provided to the farmers for the procurement of seeds, fertilizers, manure etc.  Ryat Bazar is organized for the farmers periodically.  The suggestion to the UT was that since Puducherry farming was on a reasonable scale there should be a focus on the organic farming only. Efforts should be made to eliminate the use of fertilizers and chemicals.

National Rural Drinking Water Programme

Infrastructure in Puducherry

| Sl. No. | Items | Total Nos. | Target | Achievements (as on date) | Shortfall |
| --- | --- | --- | --- | --- | --- |
| 1. | Hand pumps | - | - | - | - |
| 2. | Piped water supply schemes | 72 | 72 | 56 | - |
| 3. | Problem villages | - | - | - | - |
| 4. | Villages covered during 11th Plan | 72 | 72 | 56 | 16 |
| 5. | Slipped back habitations | 40 | 30 | 18 | 22 |

Financial Progress 2007-08 to 2009-10:

Rs. In crores

| Particulars | 2007-08 | 2008-09 | 2009 till 30.09.09 |
| --- | --- | --- | --- |
| Budget Estimates | 12.0962 | 9.5857 | 7.6621 |
| Revised Estimates | - | - | - |
| Actual Release | 12.0962 | 9.5857 | 7.6621 |

Physical Achievements (2007-08 to 2009-10)

| Particulars No. of | 2007-08 | 2008-09 | 2009-10 | Cumulative since 2005-06 | Balance |
| --- | --- | --- | --- | --- | --- |
| Uncovered Target | 42 | 15 | 20 | 194 | 20 |
| Slipped Back | 32 | 13 | 17 | 162 | - |
| Quality Affected | 10 | 2 | 3 | 32 | - |
| Total | 42 | 15 | 20 | 194 | 20 |

The UT has informed that based on the guidelines received from Government of India, 3 proposals covering 9 villages at an estimated cost of 35.34 crores have been prepared and sent to Department of Drinking Water Supply, Government of India, in order to avail CSS assistance.

Observations

Tsunami Rehabilitation and Tourism

The tourist infrastructure which includes a shopping complex, walkway and the beach protection works taken up under the TRP at Karaikal was inspected along with the district officials.  The Complex proposes to set up infrastructure which will develop both tourism and provide marketing outlets for local produce.  The auction for the shops was fixed for the same evening and the fact that the bids in the range of 300 per cent of the base rate fixed were received, indicated that this complex is going to be a successful venture.

The Karaikal Port set up in the PPP mode was also visited.  This is the single largest PPP project taken up by the State Government (along with the airport coming up in Karaikal) and it is heartening to note that two berths in the port were put up in a record time and commercial operation has already started. The State administration has provided land and necessary administrative support and the total investment has been raised by the private partner.  It goes without saying that the port will play a very important role in economic development of the state.

General Observations:

During the last two years, the actual Plan expenditure of Puducherry  has remained around Rs.1000 crores as against the approved outlays of Rs.1455 crore and Rs. 1750 crores.   For a state with very small population base and with practically no source of revenue, additional resource mobilization poses a problem.  In addition to this, the State has taken up a number of welfare measures with huge financial commitment.  The State has more number of BPL cards than there are families and support in the nature of subsidised food, items of household use, additional funding for pension schemes and additional funds under education, health and other activities have come to be established in the State.  The only way that the ballooning of expenditure under the welfare schemes can be controlled is to critically review the beneficiary group and consciously prune the population who are not poor or deserving.  This may lead to some savings which can be ploughed back to developmental activities.

Puducherry has a tremendous potential for tourism and there are several spots under the ownership of the Government, both at Kariakal and Puducherry where hotels and other tourist complexes can be developed in the PPP mode.  Similarly, large chunks of acquired land are also available very close to the port, which can be developed into a remunerative industrial hub.  Both these activities can be taken up with the state working as a facilitator.

It was also noted that the state has incurred a substantial increase in its revenue expenditure through the establishment of scores of semi Government organization like societies and companies.  There is also a huge workforce mostly in the textile sector whose output has steadily declined over the years.  As opposed to that in many areas of Government work, the work is suffering for want of manpower. The state should come out with a proper manpower deployment policy so that both the numbers and the financial commitment are frozen or reduced.

******

Planning Commission

(State Plans Division)

Subject: Implementation of the Flagship programmes in Puducherry – A report

I visited Puducherry from 3.12.2009 to 5.12.2009 alongwith the director (SP-Puducherry), to review the implementation of the flagship programmes in the UT. Review of the programmes was held in Puducherry in a meeting with Chief Secretary and other UT officials, followed by a field visit to Karaikal in Puducherry.

2. A note on the above field visit for forwarding to the PMO is enclosed.

Senior Adviser

(SP-Puducherry)

14.12.2009

Secretary Planning Commission,

P.C. U.O. No.M-13048/35/Py/2009- 14.12.2009

Copy to:

1. Member (SP- Puducherry )

2. MOS (P&PA)

No.M-13048/35/Py/-SP-2009

Planning Commission

(State Plans Division)

Subject: Implementation of the Flagship programmes in Puducherry – A report

for the PMO

Kindly find enclosed a copy of the inspection note regarding the field visit in the UT of Puducherry to review the flagship programmes in Puducherry.

JS (State Plans)

Sr. Adviser (S P – Puducherry)

Copy for information to:

- Secretary (Planning Commission)

- Member (S P – Puducherry)

Planning Commission

(State Plans Division)

Subject: Implementation of the Flagship programmes in Puducherry – A report

A report of Senior Adviser (State Plans-Puducherry), regarding the review of the implementation of the flagship programmes of the UT was sent to JS-State Plans on 14.12.2009 which was returned with a request to provide Executive Summary of the report. Accordingly, the report along with the executive summary is placed below for necessary action pl.

(Sujata Sharma)

Director

29.12.2009

JS (State Plans)

Visit of Adviser to review the implementation of the Flagship Programmes of Puducherry

A Report

Planning Commission

Yojana Bhawan

New Delhi