C O N T E N T S

| Chapter | Topic |  | Page Nos. |  |  |
| --- | --- | --- | --- | --- | --- |
| I | Preface |  | i-ii |  |  |
| II | Executive Summary |  | iii-x |  |  |
|  | II(i) | Background, Methodology | iii-iv |  |  |
|  | II(ii) | Main findings | v-x |  |  |
| Chapter –I Background of the Study, Methodology, etc. 1-11 |  |  |  |  |  |
|  | 1.1 | Background | 1-8 |  |  |
|  | 1.2 | Objectives of the Study | 8 |  |  |
|  | 1.3 | Methodology, Research Design, Reference period, Field work. | 8-11 |  |  |
| Chapter-2 Employment Assurance Scheme/Sampoorna Gram Rozgar 12-93 Yojana(SGRY) |  |  |  |  |  |
|  | 2.1 | Introduction |  | 12-14 |  |
|  | 2.2 | The Scheme, Objectives of the Scheme, Organisation, Planning, Execution, Monitoring and Evaluation |  | 14-24 |  |
|  | 2.3 | Allocation of resources |  | 24-27 |  |
|  | 2.4 | Coverage and allocation of funds at village level |  | 27-30 |  |
|  | 2.5 | Financial Progress, availability and utilization of foodgrains |  | 30-32 |  |
|  | 2.6 | Expenditure on Weaker Sections, Women, Administrative Contingencies and Trainings, Maintenance of assets created, Wages and Non-wages |  | 32-37 |  |
|  | 2.7 | Physical Progress |  | 37-38 |  |
|  | 2.8 | Asset creation |  | 38-42 |  |
|  | 2.9 | Quality, Maintenance of assets created and Muster Roll, Record of Assets created |  | 42-44 |  |
|  | 2.10 | Employment Generation, Profile of the beneficiaries, Duration of employment and Wage rate, etc. |  | 44-56 |  |
|  | 2.11 | Conclusion and suggestions |  | 57-61 |  |
|  | 2.12 | Tables (2.1 to 2.36 on EAS/SGRY) |  | 62-93 |  |