## EXECUTIVE SUMMARY

Background:

Government of India is implementing a number of Centrally Sponsored Schemes (CSS) in the areas of rural development, urban development, health and family welfare, education, agriculture, women and child development, sanitation, housing, safe drinking water, irrigation, transport, border area development, social welfare through out the Country, including Jammu and Kashmir. The main objectives of all these schemes are to generate employment, reduce poverty & economic inequality and improve the quality of life. Besides, some of these schemes aim at creation of basic infrastructure and assets essential for economic development in rural areas. Despite of the fact that huge allocations have been made by the Central Government through Centrally Sponsored Programmes in Jammu and Kashmir, the development in basic infrastructure and improvements in amenities/facilities has been inadequate, especially in rural areas of the state. The standard of living of the people has not improved to the desired extent and the employment opportunities for the youths are few and far between. Hence, it becomes imperative at this stage to know as to what extent these schemes have been in a position to achieve the stated objectives. Such an exercise will help to identify the problems/short comings in implementing these schemes. It will also help the policy makers and implementing agencies to introduce the necessary interventions to enhance the efficiency of the programme and to ensure better utilization of the resources. Hence, the Population Research Centre (PRC), Kashmir University, Srinagar, at the instance of Planning Commission, Government of India, New Delhi and Regional Evaluation Office, Chandigarh selected the following Centrally Sponsored Schemes in selected four districts of Jammu and Kashmir to assess their impact:

1.	Employment Assurance Scheme/Sampoorna Gram Rozgar Yojana

2.	Indira Awaas Yojana

3.	Swaranjayanti Gram Swarozgar Yojana

4.	Integrated Child Development Services

5.	National Old Age Pension Scheme

As per 'Terms of Reference', the detailed District Level Reports for all the five selected Centrally Sponsored Schemes have already been finalized and the findings were presented in Planning Commission. The report in hand is a State Level Evaluation Report on Employment Assurance Scheme/ Sampoorana Gram Rozgar Yojana on the basis of field study conducted in four selected districts.

Methodology

A Committee consisting of representatives of Ministry of Home Affairs, New Delhi, Programme Evaluation Organisation, New Delhi, Regional Evaluation Office, Chandigarh and Population Research Centre, Kashmir University, Srinagar was constituted to finalise the Research Design, Methodology, Questionnaire, etc. for the study. As the study in the militancy affected state of J&K was taken up  on the recommendations of the Group of Ministers on "Internal Security and Border Management", the Committee in consultation with State Government selected four districts, two each from Jammu region and Kashmir region which were either  worst affected by militancy or the border districts. In view of the objectives and Terms of References of the study, after a series of meetings of the said Committee, districts Anantnag, Kupwara, Doda and Rajouri were selected for the in-depth study. The Community Development Blocks in each district were divided into two groups of high and low performance based on the information on key indicators of development. One block from each of the two groups was selected on random basis. Detailed information about the CSS were collected from district and block offices. From each selected block, 5-7 villages were selected on random basis.  From the selected villages the information was collected  from all the beneficiaries who were covered under EAS/SGRY in the selected villages. In addition to it, from each selected village, 5 respondents who had applied, but not selected, were also interviewed. Besides, detailed interviews were held with the officials at state, district and block level. A check list was prepared to collect the qualitative information from the beneficiaries and officials/offices. The secondary data regarding the physical and financial progress of the schemes and information regarding planning, implementation and monitoring was collected from the implementing agencies of the schemes through a set of questionnaires devised for the purpose. All the questionnaires devised for the survey were finalized in consultation with the members of the Committee.

Main Findings

During the course of field work, information was collected from 53 villages covering 209 works undertaken under EAS/SGRY. Further, 209 persons who had worked as wage laborers under EAS/SGRY were also interviewed. The main findings of the study are given below:-

The primary objective of the Employment Assurance Scheme/Sampoorna Gramin Rozgar Yojana (SGRY) is to provide 100 days of assured wage employment to adult households in rural areas and thereby provide food security and improve nutritional levels. The secondary objective is to create durable community, social and economic assets and develop infrastructure in rural areas. The scheme has been subsumed with National Rural Employment Guarantee Act w.e.f. February, 2006. The main findings of the evaluation study are as follows:

- The qualitative information gathered on organizational set up in selected districts of J&K revealed that the existing organizational arrangements for planning, coordination and implementation of SGRY in Jammu and Kashmir was more or less on the same lines as indicated in the guidelines. The Panchayats were involved in the preparation of Annual Action Plans in the villages, where these were functional. However, in villages where panchayats were not functional, the Mates (contractors) were responsible for preparation of resolution of the proposed work, arranging work order, the material and labourers, execution of work, arranging payments from the block office and making payments to the labourers. These Mates were generally identified by the local MLAs and their main motive was to make profit out of the works allotted to them for execution. Hence, there was a need to eliminate Mates from the implementation of the Scheme. This could be done by holding the elections of the panchayats in the state at the earliest so that they are involved in the implementation and monitoring of the developmental schemes.

- The Annual Action Plans were not prepared strictly as per the guidelines. In most of the cases there was no evidence of preparation  of Annual Plan and planning with regards to employment generation, asset creation and allocation as per the felt needs of the people. An examination of the Annual Action Plans reflected that these were mere repetition of the earlier plans, without going into the details of available local potential, local needs, existing infrastructure etc. It was found that at village level neither the demand for wage employment was assessed nor suitable proposals were formulated for creation of useful community assets which have the potential for generating gainful employment on sustained basis. In other words, the implementing method adopted was not consistent with the intended objectives of the scheme. 	The MLAs played a vital role in finalizing the action plans and selection of mates in their respective constituencies. There was hardly any community participation in preparation of action plan, identification of the beneficiaries, supervision, 	monitoring and maintenance of the assets created under the scheme.

- There was lack of awareness about the contents and procedure for availing benefits under the Scheme among the prospective beneficiaries. Hence, there is urgent need to create awareness about the scheme among the masses and encouraging their involvement in the implementation of the scheme.

- The Vigilance & Monitoring Committees at the State, District and Block level have been constituted for overseeing the various programmes. Recently, the post of ADC has also been created in each district to closely monitor the progress of the programme. Holding Public Darbars by Deputy Commissioners is a new development to get feed back on developmental works from people. These Public Darbars have got a good response from the public and should be continued and held regularly.

- The performance of the scheme was monitored through monthly progress reports and meetings at district, division and state level.  However, in such reports/meetings, only physical and financial achievements were reported/discussed. There was no built in mechanism for field inspections, measuring quality of such works, etc. Hence , there is an immediate need to strengthen the monitoring mechanism  and identify suitable performance indicators so that there is a direct link between performance indicators and the objectives of the scheme.  There is a need to strengthen the capacity of the district and the block level agencies to generate and transmit quality data on identified parameters to aid decision-making. The use of the information technology should be encouraged for speedy transmission of data to decision-making authorities for the system to be effective. Besides, to strengthen the monitoring system, it is suggested that inspection reports should be attached with the proposal of release of grants.

- Though the guidelines were, generally, followed for allocation of funds to the districts, but certain deviations there also observed. For example Anantnag district which accounts for about 12 percent of the total rural population of the state, received around 9 percent of the funds during each of the 6 years 2000-2006. Baramulla and Jammu districts also received lesser amount allocations than their proportion of rural population in the state. On the other hand, Leh and Kargil districts, each of which  account for less than 2 percent of the total rural population of the state, received 5-6 percent of the funds, despite of the fact that the percentage  BPL families in these two districts was very low as compared to Anantnag and Baramulla districts.

- The officials pointed out that the BPL Census conducted by the state was not authentic and suggested that these BPL figures should not be used for location of funds at various levels. Hence, it is suggested that a fresh BPL Census should be conducted by Directorate of Economics and Statistics and its post enumeration check  should be assigned to four credible research organizations.

- The state utilized more than 95 percent of the funds made available to it under EAS/SGRY during 2001-07, except in 2002-03. All the selected districts also utilized more than 90 percent of funds made available to them during 2000-07. Among the four selected districts, Doda and Rajouri had better rate of utilization of funds than Kupwara and Anantnag. So far as the utilization of food grains was concerned, the state utilised more than 95 percent of the food grains lifted by it during 2001-07.

- The Scheduled Caste and Scheduled Tribe population received recommended share of allocation under EAS/SGRY in the state. Around 21-26 percent of the mandays generated under SGRY were shared by SC/ST population during 2004-06.

- Around 66079 works were undertaken in the state during 2001-04, out of which 54463 (82 percent) were completed during the same period. Similarly, out of 53606 works taken up for execution during 2004-07, 90 percent of these were completed.

- None of the sample districts/blocks/villages was found to have observed the prescribed norm of wage–material ratio (60:40) in the creation of assets. Even after fabrication, the wage–material ratio contained in the Muster rolls works out to be less than 60:40 in all the districts/blocks. An in-depth analysis of the assets created revealed that majority of the assets created were masonry works which were of capital intensive in nature, like buildings, pucca link roads, culverts, water tanks etc. Mates mentioned that it was very difficult for them to follow the guidelines for wage material ratio of 60:40 for each activity. Therefore, it is suggested that the guidelines for SGRY wage-material ratio need to be modified suitably to indicate that the ratio need to be maintained at the block level.

- On an average, around 3-4 lakh mandays were generated annually during 2000-2007 in the state. However, the data collected by the field team revealed that the information regarding number of mandays generated contained in the Muster Rolls was fabricated in such a way so as to bring conformity with the prescribed wage- material ratio as envisaged in guidelines and wage rate under SGRY and market wage rate. In no way it was the reflection of grassroot reality.

- The market wage rate per man-day in the most parts of the state even in lean agricultural season during the reference period ranged between Rs. 80-120, while as under SGRY the prescribed wage rate fixed by the government was Rs. 60. Therefore, it was difficult for the mates to engage labour on scheduled wage rates. Consequently, the laborers involved in the scheme were paid wages as per the market rates. This resulted in the creation of less number of man days but muster rolls were fabricated to show higher number of man days created. Hence, it is suggested that the execution agencies be allowed to engage the labour as per the market wage-rates and show the same in muster rolls. This will help to address the menace of fabrication of statistics in muster rolls.

- The scheme envisages that food grains should be given as part of wages under SGRY to the rural poor at the rate of 5 kg per man-day. Though the official statistics showed that all the food grains lifted by the districts were distributed among beneficiaries, but it was mentioned by large majority of beneficiaries that they did not receive any food grains as part of the wage under SGRY. It was mentioned by the Mates that generally the beneficiaries were not interested in receiving part of the wages in food grains, because they believe that the food grains provided under the scheme were of poor quality. However, the qualitative information gathered from the beneficiaries revealed that contractors sell the food grains in the open market in order to make profit out of it.  Hence, the Government should take necessary steps to remove the misconception regarding quality of food grains among wage seekers. Both print and electronic media can play a vital role in this regard. Further, there is need to monitor more closely the distribution of the food grains under SGRY or pay all the wages to the beneficiaries in cash only.

- As per guidelines of the scheme, the assets created under EAS/SGRY should be of durable nature and maintained properly to realize their potential of generation of sustainable employment. However, it was observed that assets created under EAS/SGRY were not able to generate sustainable employment. Further, it was observed that the assets created EAS/SGRY were not handed over to any agency for maintenance. Consequently, most of the assets created under the scheme were in dilapidated shape at the time of survey.

- The district and blocks level agencies have maintained complete inventory of the assets created under the programme giving details of the date of the start and the date of completion of the project, cost involved, benefits obtained, employment generated and other relevant particulars. Signboards depicting the nature of work and cost of the works were also displayed at a prominent places in the villages. The block offices have also kept photographic records of the work completed. However, the way of maintaining the records at all levels was haphazard and provides ample scope for  improvement.

- The information collected from the beneficiaries’ revealed that during 2000-2003 on an average a beneficiary was provided employment for only 17 days in Anantnag and Doda districts, 15 days in Kupwara district and 13 days in Rajouri district. Thus, none of the beneficiaries was provided wage employment for mandatory 100 days. Another issue that assumes importance in assessing the impact of EAS/SGRY is sustainability of employment and income of the beneficiaries. It was found that majority of the beneficiaries worked for less than 15 days and earned less than Rs. 1000 per annum. Thus, SGRY earnings have not adequately supplemented the household income of the beneficiaries.

Hence, it was observed that EAS/SGRY could neither provide 100 days 	generated employment nor sustained earnings each year to the beneficiaries. 	Consequently, the scheme has not been in a position to decrease the seasonal 	out-migration of laborers to other parts of the country during winter. Thus, it can be 	said that the scheme has not been in a position to achieve its objective of 	improving the economic status of 	the beneficiaries to the desired extent.