CHAPTER – VI

# MEMBER OF PARLIAMENT LOCAL AREA DEVELOPMENT PROGRAMME

Government of India introduced this scheme in 1993 where each MP (Lok Sabha and Rajya Sabha) were allotted Rs. 1.00 crore per annum to take up developmental works in the constituency. The District Collectors and Commissioners of Corporation of Chennai implement the scheme. During the last four years (1997-2001), the number of works carried out in the State is presented in Table 6.1 and 6.2.

There are 39 Lok Sabha MPs and 18 Rajya Sabha MPs in the State. During       1997-98, the allotment was made Rs. 57.00 crores and for the year 1998-99 enhanced to Rs.114 crores.  The amount released for the years 1999-2000 and 2000-2001 were        Rs. 112.00 crores each. During this period, 6052 works were carried out in the State.

| #### Table 6.1 Progress under Member of Parliament Local Area Development |  |  |  |  |
| --- | --- | --- | --- | --- |
| Scheme (MPLADS) in the State of Tamil Nadu 1997-2001 |  |  |  |  |
| # Year | Amount released (Rs. in crores) | # No. of works taken up | No. of works completed | % |
| 1997-1998 | 57 | 3210 | 2381 | 74.17 |
| 1998-1999 | 114 | 3393 | 1338 | 39.43 |
| 1999-2000 | 112 | 5171 | 5168 | 99.94 |
| 2000-2001 | 112 | 6052 | 5792 | 95.70 |
| Total | 395 | 11774 | 8887 | 75.48 |
| Source: Dept of Rural Development, Government of Tamil Nadu |  |  |  |  |

During the last four years, the government of India released Rs. 395 crores for the implementation of MPLAD. But they could not utilise the funds due to various problems viz. selection of works, implementation of works as per the guidelines, natural reasons like flood, heavy downpour, climate etc.

## Physical Achievements

District wise physical achievements are presented in Table 6.2. During the last four years (1997-2001), 14,679 works were completed. The percentage of achievement was 82. The MPs were empowered to create some critical infrastructure in his/her constituency as per the need of the population. There is no clear trend perceived as to the works, which have been taken up and completed so far. Year to year variations have been there in the works. The percentage of achievement varied from 39 to 99. During the year 1998-99, the performance was very poor. There were some districts, which registered no performance at all. It reveals that the MPs as well as the authorities, who were implementing the programmes, could not use the available fund. To make the programme a good success, the hurdles have to be identified and policies amended suitably, facilitating the utilisation of   money within the period.

### Conclusion

MPLAD was launched during 1993 and earmarked rupees one crore per annum to take up developmental works in the constituency. In response to the programme, the allocation of funds gradually were enhanced Rs.2 crores per annum. The physical achievements registered under this programme were not satisfactory due to some regional problems in execution of works. To make the program a good success, the hurdles have to be identified and policies amended suitably in an environmental perspective.