## CHAPTER – III

## JAWAHAR GRAM SAMRIDHI YOJANA

Jawahar Gram Samridhi Yojana (JGSY) was launched on April 1,1999 to ensure development of rural infrastructure at the village level by restructuring the erstwhile Jawahar Rozgar Yojana (JRY). JRY was itself a major wage employment programme launched in the year 1989 by merging the two wage employment programmes namely National Rural Employment Programme (NREP) and Rural Landless Employment Guarantee Programme (RLRGP).  It was the single largest wage employment programme implemented in all the villages of the country through the Panchayat Raj Institutions.  It also contributed to a great extend in creating the durable rural infrastructure, which was of vital importance for the development of village economy thereby improving the standard of living of the rural poor.  Both Jawahar Rozgar Yojana and Employment Assurance Scheme ensured the creation of durable assets in the form of school buildings, roads and other infrastructure.  However, under these programmes, the generation of wage employment was getting overriding priority with the result that in the process of creating employment, durable assets were created.

It was, however, felt that a stage had come when the development of village infrastructure needed to be taken up in a planned manner.  The Gram Panchayats, who were closest to the ground realities and who could effectively determine their local needs, could best do this.  Accordingly, the Government restructured Jawahar Rozgar Yojana.  The new programme Jawahar Gram Samridhi Yojana (restructured JRY), which came into effect from April 1, 1999, is dedicated entirely to the development of rural infrastructure at the village level and is being implemented by the Gram Panchayats.

# Objectives

The primary objective of JGSY is creation of demand driven community village infrastructure including durable assets at the village level with a view to enabling rural poor to have more opportunities for sustained employment.

The secondary objective of JGSY is generation of wage employment for the unemployed poor in the rural areas.

# Salient Features

# The main emphasis of JGSY is to create rural infrastructure at the village level.

- Implementation of the Jawahar Gram Samridhi Yojana entirely by the Gram Panchayat.

- Direct release of funds to the Gram Panchayats by District Rural Development Agencies (DRDAs) / Zila   Parishads (ZPs).

- Gram Panchayat is the sole authority for preparation of Annual Action Plan and its implementation with the approval of Gram Sabha.

- Empowerment of the Gram Sabha for approval of schemes/works.

- Gram Panchayat can execute works/schemes up to Rs.50000 without technical/administrative approval.  However, Gram Sabhas approval is a must.

- Twenty two and a half percent of JGSY funds are earmarked for individual beneficiary schemes for SCs/STs.

- Three percent of annual allocation would be utilized for creation of barrier free infrastructure for the disabled.

- Wages under JGSY will either be the minimum wages notified by the States or higher wages fixed by States through the prescribed procedure.

- Gram Panchayat can suitably relax 60:40 wage-material ratio for building up demand driven rural infrastructure.

- Fifteen percent of funds can be spent on maintenance of assets.

- Social Audit by the Gram Sabha

- Village level Monitoring and Vigilance Committee to oversee and supervise the work/schemes undertaken.

- DRDA/ZP is responsible for overall guidance, coordination, supervision, monitoring and periodical reporting.

# Funding pattern

Jawahar Gram Samridhi Yojana is being implemented as a centrally sponsored scheme on cost sharing basis between the Centre and the States in the ratio 75: 25.

# Works to be taken up

# All works that result in the creation of durable productive community assets can be taken up by the Gram Panchayat under Jawahar Gram Samridhi Yojana as per the felt need of the area/ people.

While creating rural infrastructure, the wage-material ratio of 60:40 prescribed under JRY has suitably been relaxed so as to enable the build up of demand driven rural infrastructure.  Care has, however, been taken to ensure that purely material oriented works are not taken up.  Simultaneously, efforts are to be made to take up labour intensive works with sustainable low cost technology.

Jawahar Gram Samridhi Yojana ensures that the following works should be given priority:

- Infrastructure for SCs/STs habitations

- Infrastructure support for Swarnjayanthi Gram Swarozgar Yojana (SGSY);

- Community infrastructure for education and health; and

- Other social, economic and physical infrastructure

The following works will not be allowed to be taken up

- Buildings for religious purposes, such as Temple, Mosque, Gurudwara, church etc.

- Monuments, Memorials, Statues, Idols, Arch gate &  Welcome Gate.

- Bridges.

- Buildings  for  higher secondary schools.

- Buildings  for  colleges.

- Desiltation of tanks.

- Black toping of roads.

### Earmarking of Resources

There is no sectoral earmarking   of   resources under JGSY, except the following:

Twenty two and a half percent of the annual allocation must be spent on individual beneficiary schemes for SCs/STs as per JGSY guidelines.  Diversion of funds meant for SCs/STs to other works is not permitted.

Three percent of the annual allocation would be utilized for creation of barrier free infrastructure for the disabled.  In case funds are not utilized under this provision, the Gram Panchayat may utilize the same for other   works under JGSY.

The State Government will be provided an amount of Rs.10 lakhs or one percent of the annual allocation, whichever is less, to meet the training expenses of officials/non-officials (Panchayat functionaries) involved in the implementation of JGSY provided that at least fifty per cent of this must be spent on the training of non-officials (Panchayat functionaries).

Financial Achievements

Table 3.1 presents the financial achievements of the schemes of JVVT/JRY and JGSY during the period 1996-2001. The State government could not execute the programmes within the stipulated period due to the natural calamities and other administrative difficulties. During the period 1996-97, the opening balance was very high and it stood at Rs. 29.87 crores. The government took some measures to reduce the spill over funds. Accordingly the spillover funds were reduced in the successive years. The spillover funds reduced from 29.87 crore to Rs. 2.63 crores upto the year 1999-2000 and there was a little set back and reached Rs. 4.06 crores during 2000-2001.

These programmes were implemented on cost sharing basis between the centre and the State government in the ratio of 75:25. During 1996-97, the total allocation made to the State was Rs. 158.05 crores and subsequently increased to Rs. 192.92 crores (1997-98). From 1998-99 onwards, the total allocation was reduced nearly half of the amount. During this period the central government rationalized the employment generation programmes and hence there was a reduction in the total allocation.

A similar trend could be seen in the category of total availability of funds. The total available funds increased during 1997-98 and further reduced from 217.45 crores to Rs. 112.91 crores. The expenditure too follows in the same pattern. In terms of percentages, the expenditure recorded more than 92% in all the years.

Table 3.2 gives a picture of physical achievements in the State during the last five years (1996-2001). These achievements were categorized under two heads viz. man-days of employment generated and the number of works completed.

In this context, man-days of employment generation gradually reduced from 488.60 lakh man-days to 137.02 lakh man-days. This has happened due to the restructuring as well as rationalizing the employment generation programmes during the period. However, the achievements recorded more than hundred percent in all the years.

The number of works carried out during the last five years fell from 48,510 to 31784. The programme has been satisfactory in terms of both financial and physical achievements.

Conclusion

JGSY is being implemented in all the blocks from April 1, 1999 onwards. The restructured employment programme ensures the development of rural infrastructure at the village level. This programme was implemented through the Panchayat Raj institution. Under this programme, the following works were carried out: infrastructure for SCs/STs habitation, infrastructure support for SGSY, community infrastructure for education and health and other social, economic and physical infrastructure. The total allocation of funds was reduced nearly half of the amount during 1998-99. The Central government took some steps for rationalizing the employment generation programmes and hence there was a reduction in the total allocation. The expenditure too follows in the same pattern and the percentage of achievement recorded more than 92% during the last five years.

During the period, the man-days of employment generation gradually came down from 488.60 lakhs to 137.02 lakhs.  However, the achievements recorded more than cent percent against the targets.  Similarly, the physical achievements too were registered hundred percent.

Through this programme, the Government created various physical assets for the use of common people.  The question which arises in the context, is as to how these infrastructures are being maintained by the Panchayat Raj institutions / elected members / collective action. One is inclined to suggest that in order to manage and preserve the common property resources in the village, a collective action is required.  The externalities of the CPRs are discussed separately in the primary data analysis of the report.